# Homepage Balance Breakdown — Full Implementation Plan

Based on: POC branch (40 files shipped), docs/homepage-balance-breakdown-shadowbox-investigation.md, and team task list.

Scope note: DeFi is excluded from the first iteration. The POC useDefiSlice exists on the branch and the DeFi column renders, but no DeFi-specific hardening work is planned until a future iteration.

## 1. Landmines & Mitigations

### L1 — Hero total vs wallet header drift (critical)

Problem: useBalanceBreakdown sums all four slices; AccountGroupBalance uses selectBalanceBySelectedAccountGroup (tokens only). The hero inside the breakdown will show a larger number than the header above it on the same screen — guaranteed “numbers don’t match” tickets within the first day.
Mitigation: Make AccountGroupBalance consume useBalanceBreakdown().hero.totalFiat when the flag is on. Same source drives both numbers.
Owner ticket: T-H1.

### L2 — USDC is treated as $1.00 (Predict) (medium)

Problem: Predict returns USDC amounts; useFiatNormalizer treats USDC as USD 1:1. During a depeg event, the breakdown overstates Predict balance.
Mitigation: Keep the 1:1 assumption behind a constant USDC_DEPEG_TOLERANCE comment. Add a remote config hook for usdc_rate_enabled if the PM decides to fetch a real USDC rate later — the plumbing is one config check in useFiatNormalizer.

### L3 — Perps WS re-render frequency (medium)

Problem: usePerpsLiveAccount can fire up to 10 Hz on volatile pairs. PERPS_HOMEPAGE_THROTTLE_MS = 1000 is applied in usePerpsSlice, but the throttle is per-subscriber — if multiple components inside the breakdown tree each call usePerpsLiveAccount, the throttle multiplies.
Mitigation: Only usePerpsSlice should call usePerpsLiveAccount. No child component should call it independently. Currently holds — enforce by lint or component API design.

## 2. Product Decisions

Decisions marked open still need a PM answer before the linked ticket can start.

### Resolved

| # | Question | Decision |
| --- | --- | --- |
| PD-1 | Does the wallet header total reflect the full portfolio? | ✅ Yes — header = full portfolio. T-H1 implements this. |
| PD-2 | Which Perps number in the slice total? | ✅ totalBalance / equity (includes uPnL) — implemented in POC. |
| PD-3 | Which Predict number in the slice total? | ✅ availableBalance + Σ position.currentValue — implemented in POC. |
| PD-4 | Predict active bets: cost-basis vs mark? | ✅ Mark (currentValue) — what the API returns today. |
| PD-5 | Full screen or bottom sheet? | ✅ Full screen — stack navigation already in place. |

### Open

| # | Question | Options | Recommendation |
| --- | --- | --- | --- |
| PD-6 | How are geo-blocked / ineligible users shown? | (A) Row hidden entirely (B) Row greyed as “Not available in your region” (C) Row shown with $0 | Implemented as B; needs copy approval from PM |
| PD-7 | USDC peg assumption for Predict balances? | (A) 1 USDC = $1.00 USD (B) Fetch live rate | A for now — flag for PM review |

## 3. Tickets + ETA

Sizing: 1 senior mobile dev familiar with the controller architecture + 1 QA/E2E resource.
Calendar day estimates are from merge of POC to production-ready PR.
Items marked ✅ Done in POC are complete and tested.

### Phase 0 — POC (already shipped on branch)

The POC covers ~40 files and implements the full end-to-end feature flow:

UI components: BreakdownDonutChart (dim, segment gap), BreakdownHeroValue (count-up animation, adjustsFontSizeToFit), BreakdownLegend (animated enter/exit), BreakdownListItem (avatar, progress bar, delta, P&L %), BreakdownDrilldownList (skeleton + error states), BreakdownActionFooter (CTA buttons).

Data hooks: useTokensSlice (symbol grouping, top-N drilldown, 1d delta), usePerpsSlice (MtM positions, category grouping, session uPnL fallback), usePredictSlice (available balance + open positions by category), useDefiSlice (protocol grouping, poll on mount — not hardened in iteration 1), useBalanceBreakdown (central aggregator: theme colors, percentages, hero delta), useFiatNormalizer (USD/USDC → user currency).

Integration: Full navigation stack wired (MainNavigator → BalanceBreakdownScreen), feature-flagged tap-to-breakdown on AccountGroupBalance, theme-aware slice and donut colors from useTheme(), privacy mode masking on all hero and drilldown values, analytics events for open, slice tap, and drilldown CTA tap.

Tests: 51 unit tests across all hooks, utils, and the view; E2E smoke spec covering open, overview, drilldown, and CTA navigation.

### Phase 1 — Production readiness (target: 1-2 weeks)

#### Block 0 — POC code polish (do first, unblocks everything)

| # | Ticket | Scope | ETA |
| --- | --- | --- | --- |
| T-POLISH | Full pass over all POC files: remove debug artefacts and console.logs, resolve inline TODOs, enforce strict TypeScript (no implicit any), normalise naming conventions, ensure no hardcoded test values remain, verify file/component organisation matches team standards | All BalanceBreakdown/ files | 2 d |

#### Block A — Hero reconciliation

| # | Ticket | Scope | ETA |
| --- | --- | --- | --- |
| T-H1 | Wire AccountGroupBalance header to consume useBalanceBreakdown().hero.totalFiat when homepageBalanceBreakdownEnabled is on | AccountGroupBalance.tsx, useBalanceBreakdown | 1 d |
| T-H2 | Update AccountGroupBalanceChange 1d delta on the header to use useBalanceBreakdown().hero.delta when breakdown enabled | AccountGroupBalance.tsx | 0.5 d |

#### Block B — UX polish

| # | Ticket | Scope | ETA |
| --- | --- | --- | --- |
| T-U3 | Add retry/error-state affordance on slice rows with status='error' — small inline error icon + pull-to-refresh copy update | BreakdownLegend.tsx, BreakdownListItem.tsx | 0.5 d |
| T-U4 | BreakdownActionFooter: add navigation targets for Perps and Predict slices (currently only Tokens + DeFi have routes); confirm routes with PM | BreakdownActionFooter.tsx, SLICE_NAV_CONFIG | 0.5 d |
| T-U5 | Confirm and QA privacy mode masking on heroSupplementalPnlText; ensure Analytics events don’t leak raw values in privacy mode | BreakdownHeroValue.tsx, analytics events | 0.5 d |

#### Block C — Cleanup

| # | Ticket | Scope | ETA |
| --- | --- | --- | --- |
| T-TOKEN-2 | Verify homepageSectionsV1Enabled guard in useTokensSlice is still correct once flag is graduated; remove guard or rename selector | useTokensSlice.ts | 0.5 d |

#### Block D — Testing & analytics

| # | Ticket | Scope | ETA |
| --- | --- | --- | --- |
| T-QA1 | Expand E2E smoke spec: drilldown for Perps and Predict legend rows; CTA navigation for each; add geo-blocked fixture (Predict/Perps ineligible) | balance-breakdown.spec.ts, BalanceBreakdownView.ts POM, fixtures | 3 d |
| T-QA2 | Unit tests: privacy-mode leakage guard on analytics events, USDC 1:1 conversion passthrough | useBalanceBreakdown.test.ts, slice hook tests | 0.5 d |
| T-QA3 | Analytics: confirm BALANCE_BREAKDOWN_SLICE_TAPPED fires for donut-tap path; add source: 'donut' property | BalanceBreakdownView.tsx | 0.5 d |
| T-QA4 | Reassure snapshot for BalanceBreakdownView with all four slices loading + drilldown switch | tests/reassure/ | 0.5 d |

Phase 1 total: ~10 working days (~2 calendar weeks).

### Phase 2 — Production hardening

| # | Ticket | Scope | ETA |
| --- | --- | --- | --- |
| T-H4 | Graduate homepageBalanceBreakdownEnabled from remote flag to shipped; clean up flag selector and conditional branches | featureFlagController/homepage/index.ts, AccountGroupBalance.tsx | 1 d |
| T-PERF2 | Audit selectBalanceBySelectedAccountGroup memoization in breakdown context; ensure popularChainIds ref is stable (mirror AccountGroupBalance.tsx popularChainIdsKey pattern) | useTokensSlice.ts | 0.5 d |
| T-UNIFY1 | Migrate remaining callers of useGetTotalFiatBalanceCrossChains to selectBalanceBySelectedAccountGroup to kill dual-pipeline drift permanently | Cross-app, high coordination risk | 5 d |
| T-PRIV1 | Unified privacy-mode contract: define a single usePrivacyAwareFormat(value, currency) hook used by all slices so masking behavior is consistent | New hook, replace per-component getPrivacyMaskText calls | 2 d |

Phase 2 total: ~9 working days (~2 calendar weeks).

## 4. Recommended Delivery Order

Week 1     T-POLISH (2d) — POC code polish, unblocks all other work
           T-H1 (1d), T-H2 (0.5d) — reconcile header
           T-U4 (0.5d) — action footer routes

Week 2     T-U3 (0.5d), T-U5 (0.5d) — UX polish
           T-TOKEN-2 (0.5d) — cleanup
           T-QA2 (0.5d), T-QA3 (0.5d) — fast unit/analytics tests
           T-QA4 (0.5d) — Reassure snapshot
           [QA runs T-QA1 in parallel across both weeks — 3d]
           → Feature-flag enabled for internal dogfood

Week 3–4   Phase 1 QA, bug bash, geo-blocked device testing
           → Phase 1 ships

Week 5–7   Phase 2:
           T-H4 (1d) → T-PERF2 (0.5d) → T-PRIV1 (2d) → T-UNIFY1 (5d)*
           (* high blast-radius — start cross-team coordination in Week 3)

Ongoing    Phase 3 picked up as capacity allows

## 5. Open Questions for Engineering

- T-UNIFY1 blast radius: migrating useGetTotalFiatBalanceCrossChains callers touches screens outside the breakdown. Does this need a canary / A/B release, or a single coordinated PR with the assets team?

- DeFi iteration 2 scope: once DeFi is back in scope, deferred items are: stale-data UX (defi_stale warning + “last updated Xm ago”), useFocusEffect re-poll on screen focus, event-driven invalidation on transactionConfirmed, DeFi selector shallow-equal memoization, receipt-token dedupe (aToken/cToken double-count between TokensController and DeFiPositionsController), and per-protocol icons in drilldown rows.